## Sheet1
Masters Dissertation Timeline
Project: "Expanding the Proof Rule Base of the AtelierB Automated Prover"
by Agata Borkowska, u1690550, MSc Computer Science, University of Warwick
|  |  |  | Estimated duration | [6 empty] | Busy Period |  |  |  |  | Very Busy Period
Task | Start | Duration | Weeks (numbering follows the University weeks convention)
|  |  | Spring Term | [14 empty] | Summer Term
|  |  | 9th January - 18th March | [14 empty] | 24th April - 1st July
|  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Literature Review | 15 | 4 | bar: 9th January - 18th March 15 to 9th January - 18th March 18; 24th April - 1st July 33 to 24th April - 1st July 35
Project proposal | 17 | 5 | bar: 9th January - 18th March 17 to 9th January - 18th March 21; 24th April - 1st July 33 to 24th April - 1st July 35
Review of existing rules | 22 | 2 | bar: 9th January - 18th March 22 to 9th January - 18th March 24; 24th April - 1st July 33 to 24th April - 1st July 35
Choosing example scenarios | 23 | 2 | bar: 9th January - 18th March 23 to 9th January - 18th March 24; 24th April - 1st July 33 to 24th April - 1st July 35
Identifying most commonly unproven POs | 25 | 3 | bar: 9th January - 18th March 24 to 9th January - 18th March 27; 24th April - 1st July 33 to 24th April - 1st July 35
Review of methods for verifying user-created rules | 27 | 3 | bar: 9th January - 18th March 28 to 24th April - 1st July 31; 24th April - 1st July 33 to 24th April - 1st July 35
Project Presentation | 30 | 1 | bar: 24th April - 1st July 30 to 24th April - 1st July 31; 24th April - 1st July 33 to 24th April - 1st July 35
Close inspection of the behaviour of the prover | 36 | 4 | bar: 24th April - 1st July 33 to 24th April - 1st July 39
Exploring new tactics | 38 | 5 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 38 to 24th April - 1st July 42
Interim Report | 39 | 2 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 39 to 24th April - 1st July 40
Comaprison to BEval and other software | 42 | 3 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 42 to 24th April - 1st July 44
Response to above/to other things that came up | 33 | 3 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 44 to 24th April - 1st July 46
Benchmarking | 47 | 2 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 47 to 24th April - 1st July 48
Polishing writeup | 48 | 3 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 48 to 24th April - 1st July 50
Submission | 51 | 1 | bar: 24th April - 1st July 33 to 24th April - 1st July 35; 24th April - 1st July 51